## Sheet1
Estimated total effort | 49
Days of sprint | 7
Daily estimated effort | 7
Number of team members | 3
day | Member 1 | Member 2 | Member 3 | Total Actual Daily Effort | Actual Remaining Effort | Estimated Remaining Effort
0 |  |  |  | 0 | 49 | 49
1 |  |  |  | 0 | 49 | 42
2 | 5 | 5 |  | 10 | 39 | 35
3 | 2 | 2 |  | 4 | 35 | 28
4 |  |  | 1 | 1 | 34 | 21
5 | 10 | 2 | 2 | 14 | 20 | 14
6 | 5 | 3 | 5 | 13 | 7 | 7
7 | 0 | 2 | 5 | 7 | 0 | 0