## Sheet1
Estimated total effort | 17
Days of sprint | 7
Daily estimated effort | 2.4286
Number of team members | 3
day | Member 1 | Member 2 | Member 3 | Total Actual Daily Effort | Actual Remaining Effort | Estimated Remaining Effort
0 |  |  |  | 0 | 17 | 17
1 |  |  |  | 0 | 17 | 14.5714
2 | 5 |  |  | 5 | 12 | 12.1429
3 | 2 |  |  | 2 | 10 | 9.7143
4 |  |  |  | 0 | 10 | 7.2857
5 | 10 |  |  | 10 | 0 | 4.8571
6 |  |  |  | 0 | 0 | 2.4286
7 |  |  |  | 0 | 0 | 0